## Slide 1: Artificial Intelligence POC
Co-developing an AI Platform via the Absa Innovation Hubs
7th July 2026
Nchimunya Munyama

## Slide 2: Vision & Opportunity Customer Lifecycle Prediction Customer Value Intelligence Validate AI business value
Identify lifecycle stage, churn risk, and next-best actions to improve retention and engagement.
Predict balance growth, identify high-value customers, and detect value erosion risks.
Deliver working AI models, dashboards, KPIs, and a roadmap for enterprise rollout.
Transforming Data into Predictive Intelligence
Develop two high-impact AI use cases focused on customer growth and retention.
Demonstrate measurable business value through a 90-day Proof of Concept.
A
B
C

## Slide 3: 90-Day PoC Roadmap
Discovery & Design
Define use cases and KPIs
Assess customer data sources
Establish success criteria
Data Foundation
Prepare and consolidate data
Create unified analytical datasets
Engineer model features
Model Development
Develop lifecycle prediction models
Build customer value scoring
Create balance forecasting capabilities
3
Validation & Pilot
Test with business users
Validate model performance
Present business case and rollout roadmap
4
From Data to Business Value
Focus on Customer Lifecycle Prediction and Customer Value Intelligence.
Deliver validated models, dashboards, and measurable business outcomes
2
1
Notes: Please update with our icons

## Slide 4
Outcome Table For PoC – 3 Month Projection
Workstream | Deliverables | Details / Outcome | Timeline
Data Access & Compliance | • Data integration completed • Compliance review completed | Secure access to anonymised customer, transactional, and product data. Data access aligned with Absa's governance, privacy, and security requirements. | Month 1
Business Discovery & Use Case Design | • Customer Lifecycle framework • Customer Value framework • KPI baseline established | Define customer lifecycle stages, customer value methodology, business objectives, success measures, and model requirements. | Month 1
Customer Lifecycle Prediction Development | • Lifecycle segmentation model • Churn prediction model • Next-best-action engine | AI model developed to identify customer lifecycle stages, predict churn risk, and recommend proactive engagement actions to Relationship Managers. | Month 1–2
Customer Value & Balance Intelligence Development | • Customer value scoring model • Balance growth prediction model • Opportunity recommendation engine | AI model developed to identify future high-value customers, forecast balance growth, and detect potential balance erosion risks. | Month 1–2
Model Validation & Optimisation | • Feature engineering • Model tuning • Explainability assessment | Improve model accuracy, interpretability, and business usability. Feature importance and model drivers documented for transparency and governance. | Month 2–3
Dashboard Development | • Dashboard v1 Wireframe • Interactive Dashboard v2 | Development of AI dashboards providing lifecycle insights, churn risk monitoring, customer value scoring, balance forecasts, and opportunity recommendations. | Month 1–3
Stakeholder Engagement | • Business workshops • Demonstration sessions • Feedback incorporation | Regular engagement with Relationship Managers, Product Teams, CRM Teams, and Executives to validate outputs and refine dashboards. | Month 2–3
Pilot Testing & Evaluation | • User acceptance testing • Business validation • KPI assessment | Validate model performance against agreed business outcomes and test usability with selected business users. | Month 3
Documentation & Knowledge Transfer | • Technical documentation • User guide • Knowledge transfer workshop | Documentation of models, dashboards, methodologies, and operational procedures to support future scaling. | Month 3
Final PoC Report & Roadmap | • Executive summary • Business case • Production roadmap | Presentation of business value achieved, lessons learned, ROI opportunities, risks, and recommendations for enterprise deployment. | End of Month 3

## Slide 5
Tracking KPIs Table For 3 Month PoC
KPI / Output | Description | Target Value / Criteria | Timeframe
Customer Lifecycle Prediction Model Developed | Build and validate AI models that classify customers across lifecycle stages. | Model operational and validated for pilot use. | End of Month 2
Customer Value Intelligence Model Developed | Develop customer value scoring and balance prediction capability. | Model operational and validated for pilot use. | End of Month 2
3Churn Prediction Accuracy | Measure the model's ability to identify customers at risk of attrition. | ≥ 80% prediction accuracy | End of Month 3
Customer Value Prediction Accuracy | Measure the effectiveness of customer value and growth forecasting. | ≥ 80% prediction accuracy | End of Month 3
Next-Best-Action Recommendations | Generate business recommendations for customer engagement and growth. | Automated recommendations available within dashboard | End of Month 3
Dashboard Functionality Completion | Deliver executive and operational dashboards displaying AI insights. | Interactive dashboard fully operational | End of Month 3
Stakeholder Engagement Sessions | Gather business feedback and validate outputs. | Minimum 3 workshops and demonstrations completed | By Month 3
Governance & Compliance Alignment | Ensure adherence to data privacy, ethical AI, and internal governance requirements. | 100% compliance sign-off achieved | By Month 2
Internal User Pilot Testing | Validate business usability with Relationship Managers and selected users. | Minimum 10 pilot users actively participating | By Month 3